## Credentials
SENTINELLOG — CREDENTIALS & ACCESS
Category | Item | Value | Access Level | Source
App Login | Admin | admin / Admin@12345! | Full access - all pages & API | SeedUser.cs
App Login | Analyst | analyst / Analyst@12345! | Read + search + alerts | SeedUser.cs
App Login | ReadOnly | readonly / ReadOnly@12345! | Read-only dashboard | SeedUser.cs
API Auth | POST /api/auth/login | {"username":"admin","password":"Admin@12345!"} | Returns JWT Bearer token | AuthController
API Auth | JWT Header | Authorization: Bearer <token> | All /api/* endpoints
Database | Host | jsw-ams.c5pwstwpokkz.ap-south-1.rds.amazonaws.com | PostgreSQL on AWS RDS | appsettings.json
Database | Username / Password | postgres / u0MjCOVeTvx40ZhRBCV1 | Database: Syslog | appsettings.json
URLs | API | https://localhost:5001 (or http://localhost:5000) | REST API + Swagger | launchSettings.json
URLs | WebUI | https://localhost:5003 (or http://localhost:5002) | MVC Web Application | launchSettings.json
URLs | Worker | Console app / Windows Service | Background processor | launchSettings.json

## UI Pages
UI PAGES - MODULE TRACKER (Mockup vs Implementation)
# | Page / Module | Route | Mockup Reference | Status | % Done | Gap Summary | Priority | Complexity | Assigned To
1 | Homepage / Landing | / | sentinellog-homepage.html | PARTIAL | 60% | Missing: SSO button, real MFA, password toggle, forgot password, live ticker, hero stats from API, demo video modal | HIGH | MEDIUM
2 | Dashboard Overview | /dashboard | syslog-dashboard.html | PARTIAL | 65% | Missing: Donut chart, Source Types sparklines, Device Health panel, trend arrows on KPIs, Export & +New Alert buttons | HIGH | MEDIUM
3 | Live Feed | /dashboard/livefeed | syslog-dashboard.html | PARTIAL | 55% | Missing: Search bar, Source dropdown, Time Range dropdown, Facility column, streaming footer bar, Export button, row left-border | HIGH | MEDIUM
4 | Log Search | /dashboard/search | syslog-dashboard.html | PARTIAL | 45% | Missing: Keyword/Severity/SourceType/Facility/CIDR filters, active filter tags, facet sidebar, sort dropdown, CSV export | HIGH | HIGH
5 | Analytics | /dashboard/analytics | syslog-dashboard.html | PARTIAL | 40% | Missing: Event Rate line chart, Heatmap (hour x day), Security Categories, Top Talkers Volume+Trend columns | MEDIUM | HIGH
6 | Alerts | /dashboard/alerts | syslog-dashboard.html | PARTIAL | 35% | Missing: Rule cards layout, enable/disable toggle, notification chips, +New Rule modal, Edit modal, Channels sidebar, Summary sidebar | HIGH | HIGH
7 | Storage | /dashboard/storage | syslog-dashboard.html | PARTIAL | 50% | Missing: Log Rotation Schedule, Storage Growth chart, progress bars on KPIs, archive/delete columns | MEDIUM | MEDIUM
8 | Sources - Inventory | /sources | sentinellog-sources-settings.html | PARTIAL | 50% | Missing: Search+filter toolbar, checkbox column, EPS bars, relative time, hover actions, pagination, Add Source modal, Detail panel | HIGH | HIGH
9 | Sources - Groups | /sources/groups | sentinellog-sources-settings.html | STUB | 5% | Entire page placeholder. Need: Group cards grid with icon, host count, EPS, events/24h, status, View/Edit buttons | MEDIUM | MEDIUM
10 | Sources - Protocols | /sources/protocols | sentinellog-sources-settings.html | STUB | 5% | Entire page placeholder. Need: Listening Ports table, Network Access Control panel with toggles + rate limit | LOW | MEDIUM
11 | Sources - Parsers | /sources/parsers | sentinellog-sources-settings.html | STUB | 5% | Entire page placeholder. Need: Draggable parser cards with priority, format, source count, Edit/Test, +New Parser | LOW | HIGH
12 | Settings - General | /settings/general | sentinellog-sources-settings.html | IMPLEMENTED | 80% | Missing: Instance ID display, Accent Color picker, separate card grouping | LOW | LOW
13 | Settings - Network | /settings/network | sentinellog-sources-settings.html | STUB | 5% | Entire page placeholder. Need: TLS/SSL Certificates card, Listener Bindings, mTLS toggle, TLS version dropdown | MEDIUM | HIGH
14 | Settings - Notifications | /settings/notifications | sentinellog-sources-settings.html | STUB | 5% | Entire page placeholder. Need: SMTP Email card+test, SNMP Trap card, Webhook/PagerDuty card+test | MEDIUM | HIGH
15 | Settings - Users | /settings/users | sentinellog-sources-settings.html | PARTIAL | 60% | Missing: Invite User modal, MFA column, role editing, LDAP/AD sync, session timeout, auth policy card | HIGH | MEDIUM
16 | Settings - API Keys | /settings/api | sentinellog-sources-settings.html | STUB | 5% | Entire page placeholder. Need: Generate Key, key display+copy, External Integrations grid | LOW | MEDIUM
17 | Settings - Audit Log | /settings/audit | sentinellog-sources-settings.html | STUB | 5% | Entire page placeholder. Need: Audit entries list, user+action filters, export button | MEDIUM | MEDIUM
18 | Settings - License | /settings/license | sentinellog-sources-settings.html | PARTIAL | 40% | Has basic display. Missing: Usage bars, license key+copy, Upload/Upgrade buttons, Danger Zone | LOW | LOW
19 | Sidebar Navigation | All pages | All mockups | IMPLEMENTED | 90% | Missing: Dynamic badge counts from real data | LOW | LOW
20 | Topbar | All pages | All mockups | IMPLEMENTED | 85% | Missing: Export CSV, +Add buttons per page, dynamic EPS from metrics | LOW | LOW

## Component Detail
UI COMPONENT DETAIL - Per Page Tracking
# | Page | Component | Mockup Source | Implemented? | Notes
-- HOMEPAGE --
1 | Homepage | Top Nav Bar (Features/Platform/Security/Docs) | homepage | NO | No top nav - jumps to hero
2 | Homepage | Hero Section with scan-line animation | homepage | PARTIAL | Hero exists but no scan-line CSS
3 | Homepage | Hero Stats (5000+ EPS, 100TB, <2s, NERC CIP) | homepage | PARTIAL | Stats bar exists but hardcoded values
4 | Homepage | Login Card - Username/Password form | homepage | YES | Working with JWT auth
5 | Homepage | Login Card - Password visibility toggle | homepage | NO | Not implemented
6 | Homepage | Login Card - Remember device checkbox | homepage | YES | Exists in form
7 | Homepage | Login Card - Forgot Password link | homepage | NO | No backend flow
8 | Homepage | Login Card - SSO / Active Directory button | homepage | NO | Button not present
9 | Homepage | Login Card - TLS 1.3 badge | homepage | NO | Not shown
10 | Homepage | MFA Screen (6-digit OTP) | homepage | PARTIAL | UI exists but backend returns success always
11 | Homepage | Live Log Ticker (animated marquee) | homepage | NO | Not implemented
12 | Homepage | Feature Cards Grid (6 cards) | homepage | YES | Implemented with icons
13 | Homepage | CTA Section | homepage | PARTIAL | No Schedule Demo modal
14 | Homepage | Footer with status badge | homepage | PARTIAL | No live operational check
-- DASHBOARD --
15 | Dashboard | 6 KPI Metric Cards | dashboard | YES | All 6 from API
16 | Dashboard | KPI Trend Indicators (up 12%, down 3%) | dashboard | NO | No trend calc
17 | Dashboard | Event Volume Bar Chart (24h) | dashboard | YES | Chart.js stacked bar
18 | Dashboard | Bar Chart - By Severity/Source toggle | dashboard | NO | Only By Severity
19 | Dashboard | Top Sources Panel (list with bars) | dashboard | YES | Working
20 | Dashboard | Recent Alerts Table | dashboard | YES | Working
21 | Dashboard | Severity Breakdown Donut Chart | dashboard | NO | Mockup has SVG donut
22 | Dashboard | Source Types Sparklines Panel | dashboard | NO | Not implemented
23 | Dashboard | Device Health Panel | dashboard | NO | Not implemented
-- LIVE FEED --
24 | Live Feed | Severity Filter Buttons | dashboard | YES | Working
25 | Live Feed | Search Bar in toolbar | dashboard | NO | Not implemented
26 | Live Feed | Source Dropdown filter | dashboard | NO | Not implemented
27 | Live Feed | Time Range Dropdown | dashboard | NO | Not implemented
28 | Live Feed | Stats display (showing X/Y, crit, err) | dashboard | PARTIAL | Only row count
29 | Live Feed | Pause/Resume button | dashboard | YES | Working
30 | Live Feed | Facility column | dashboard | NO | Not in table
31 | Live Feed | Row left-border severity coloring | dashboard | NO | Class exists, no CSS rule
32 | Live Feed | Footer bar (LIVE, Rate, Buffer, Filtered) | dashboard | NO | Not implemented
33 | Live Feed | Export button | dashboard | NO | Not implemented
-- SEARCH --
34 | Search | Host / Program / Source IP / Date filters | dashboard | YES | Working inputs
35 | Search | Keyword / Message filter | dashboard | NO | Not implemented
36 | Search | Severity dropdown | dashboard | NO | Not implemented
37 | Search | Source Type dropdown | dashboard | NO | Not implemented
38 | Search | Facility dropdown | dashboard | NO | Not implemented
39 | Search | IP/CIDR filter | dashboard | NO | Not implemented
40 | Search | Active filter tags with remove | dashboard | NO | Not implemented
41 | Search | Facet sidebar (severity/source/facility) | dashboard | NO | Not implemented
42 | Search | Sort dropdown (Newest/Oldest) | dashboard | NO | Not implemented
43 | Search | CSV Export button | dashboard | NO | Not implemented
44 | Search | Result count + query time | dashboard | PARTIAL | Count yes, time no
45 | Search | Pagination | dashboard | YES | Working
-- ANALYTICS --
46 | Analytics | Event Volume Bar Chart (24h) | dashboard | YES | Chart.js bar
47 | Analytics | Event Rate Line Chart (multi-severity area) | dashboard | NO | Not implemented
48 | Analytics | Severity Breakdown Sparklines | dashboard | YES | Working
49 | Analytics | Top Talkers Table | dashboard | YES | Working basic
50 | Analytics | Top Talkers Volume + Trend columns | dashboard | NO | Not implemented
51 | Analytics | Heatmap (hour x day) | dashboard | NO | Not implemented
52 | Analytics | Security Event Categories | dashboard | NO | Not implemented
53 | Analytics | Time range + bucket dropdowns | dashboard | PARTIAL | Range dropdown exists, no bucket
-- ALERTS --
54 | Alerts | Alert KPI Cards (Crit/Warn/Active/Resolved) | dashboard | YES | 4 cards from API
55 | Alerts | Fired Events Table + Ack button | dashboard | YES | Working
56 | Alerts | Alert Rules Table | dashboard | PARTIAL | Flat table - mockup has cards
57 | Alerts | Rule Enable/Disable Toggle | dashboard | NO | API exists, no UI toggle
58 | Alerts | Notification Channel chips on rules | dashboard | NO | Not implemented
59 | Alerts | + New Rule Modal / Form | dashboard | NO | TODO stub
60 | Alerts | Edit Rule Modal | dashboard | NO | Not implemented
61 | Alerts | Notification Channels sidebar | dashboard | NO | Whole panel missing
62 | Alerts | Alert Summary Today sidebar | dashboard | NO | Data in cards, not sidebar layout
-- STORAGE --
63 | Storage | Storage KPI Cards (Primary/Archive/Rate/Compression) | dashboard | YES | Working
64 | Storage | Retention Policies Table | dashboard | YES | Working
65 | Storage | Progress bars on KPI cards | dashboard | NO | Not implemented
66 | Storage | Log Rotation Schedule table | dashboard | NO | Not implemented
67 | Storage | Storage Growth 30-day chart | dashboard | NO | Not implemented
-- SOURCES --
68 | Sources | Source KPI Cards (5 cards) | sources-settings | YES | Working from API
69 | Sources | Sources Inventory Table | sources-settings | YES | Basic table
70 | Sources | Sub-tabs (Inventory/Groups/Protocols/Parsers) | sources-settings | YES | Routes exist, 3 are stubs
71 | Sources | Toolbar search + filter dropdowns | sources-settings | NO | Not implemented
72 | Sources | Checkbox column for bulk actions | sources-settings | NO | Not implemented
73 | Sources | EPS bar in table | sources-settings | NO | Not implemented
74 | Sources | Relative time Last Event | sources-settings | NO | Raw datetime shown
75 | Sources | Row hover actions (Edit/Delete) | sources-settings | NO | Not implemented
76 | Sources | Pagination | sources-settings | NO | Not on sources page
77 | Sources | + Add Source button + Modal | sources-settings | NO | API exists, no UI
78 | Sources | Source Detail Slide-in Panel | sources-settings | NO | Not implemented
79 | Sources | Groups cards grid | sources-settings | NO | Stub page
80 | Sources | Protocols table + Network ACL | sources-settings | NO | Stub page
81 | Sources | Parsers draggable cards | sources-settings | NO | Stub page
-- SETTINGS --
82 | Settings | General - Platform Identity card | sources-settings | YES | Working form
83 | Settings | General - Time & Locale card | sources-settings | YES | Working
84 | Settings | General - Display & UI card | sources-settings | YES | Working
85 | Settings | General - Accent Color picker | sources-settings | NO | Not implemented
86 | Settings | Network - TLS/SSL Certificates | sources-settings | NO | Stub page
87 | Settings | Network - Listener Bindings | sources-settings | NO | Stub page
88 | Settings | Notifications - SMTP Email + test | sources-settings | NO | Stub page
89 | Settings | Notifications - SNMP Trap Forwarding | sources-settings | NO | Stub page
90 | Settings | Notifications - Webhook/PagerDuty + test | sources-settings | NO | Stub page
91 | Settings | Users - User accounts table | sources-settings | YES | Working with delete
92 | Settings | Users - Invite User modal | sources-settings | NO | Not implemented
93 | Settings | Users - MFA column + toggle | sources-settings | NO | Not in table
94 | Settings | Users - Role assignment | sources-settings | NO | Shown but not editable
95 | Settings | Users - LDAP/AD sync toggle | sources-settings | NO | Not implemented
96 | Settings | Users - Auth Policy card | sources-settings | NO | Not implemented
97 | Settings | API Keys - Generate + display + copy | sources-settings | NO | Stub page
98 | Settings | API Keys - External Integrations grid | sources-settings | NO | Stub page
99 | Settings | Audit Log - Entries list + filters | sources-settings | NO | Stub page
100 | Settings | License - Usage bars (%) | sources-settings | NO | Basic display only
101 | Settings | License - Key display + copy | sources-settings | NO | Not implemented
102 | Settings | License - Upload/Upgrade/Danger Zone | sources-settings | NO | Not implemented

## API Endpoints
API ENDPOINTS - IMPLEMENTATION STATUS
# | Method | Endpoint | Controller | Status | UI Wired? | Notes
1 | POST | /api/auth/login | AuthController | DONE | YES | JWT + refresh token rotation
2 | POST | /api/auth/refresh | AuthController | DONE | YES | Single-use token rotation
3 | POST | /api/auth/logout | AuthController | DONE | YES | Revokes refresh token
4 | POST | /api/auth/verify-mfa | AuthController | STUB | PARTIAL | Always returns success - no real TOTP
5 | GET | /api/logs/dashboard/summary | LogsController | DONE | YES | Dashboard KPIs
6 | GET | /api/logs/live | LogsController | DONE | YES | Live feed polling
7 | GET | /api/logs/search | LogsController | DONE | YES | Search with filters
8 | POST | /api/logs/search | LogsController | DONE | NO | JSON body search - not used by UI
9 | GET | /api/logs/analytics/event-volume | LogsController | DONE | YES | Bar chart data
10 | GET | /api/logs/analytics/severity-breakdown | LogsController | DONE | YES | Sparkline data
11 | GET | /api/logs/analytics/top-talkers | LogsController | DONE | YES | Top talkers list
12 | GET | /api/sources | SourcesController | DONE | YES | Paginated sources
13 | GET | /api/sources/summary | SourcesController | DONE | YES | KPI counts
14 | GET | /api/sources/{id} | SourcesController | DONE | NO | No detail panel in UI
15 | POST | /api/sources | SourcesController | DONE | NO | No Add Source modal in UI
16 | PUT | /api/sources/{id} | SourcesController | DONE | NO | No Edit Source UI
17 | PATCH | /api/sources/{id}/status | SourcesController | DONE | NO | No status toggle in UI
18 | DELETE | /api/sources/{id} | SourcesController | DONE | NO | No delete button in UI
19 | GET | /api/alerts/rules | AlertsController | DONE | YES | Rules table
20 | GET | /api/alerts/rules/{id} | AlertsController | DONE | NO | No detail view
21 | POST | /api/alerts/rules | AlertsController | DONE | NO | No create modal
22 | PUT | /api/alerts/rules/{id} | AlertsController | DONE | NO | No edit modal
23 | PATCH | /api/alerts/rules/{id}/toggle | AlertsController | DONE | NO | No toggle in UI
24 | DELETE | /api/alerts/rules/{id} | AlertsController | DONE | NO | No delete button
25 | GET | /api/alerts/events | AlertsController | DONE | YES | Fired events table
26 | GET | /api/alerts/events/{id} | AlertsController | DONE | NO | No detail view
27 | PATCH | /api/alerts/events/{id}/acknowledge | AlertsController | DONE | YES | Ack button works
28 | GET | /api/alerts/summary | AlertsController | DONE | YES | KPI cards
29 | GET | /api/users | UsersController | DONE | YES | Users table
30 | GET | /api/users/{id} | UsersController | DONE | NO | No detail view
31 | POST | /api/users | UsersController | DONE | NO | No Invite User modal
32 | PUT | /api/users/{id} | UsersController | DONE | NO | No edit form
33 | DELETE | /api/users/{id} | UsersController | DONE | YES | Delete button works
34 | GET | /api/settings | SettingsController | DONE | YES | General settings form
35 | PUT | /api/settings | SettingsController | DONE | YES | Save settings
36 | GET | /api/settings/storage | SettingsController | DONE | YES | Storage KPIs
37 | GET | /api/settings/storage/policies | SettingsController | DONE | YES | Retention table
38 | PUT | /api/settings/storage/policies | SettingsController | DONE | NO | No create/edit policy UI
39 | GET | /api/settings/metrics | SettingsController | DONE | NO | Not wired to any chart
40 | GET | /api/settings/system-logs | SettingsController | DONE | NO | Could power audit log page

## Worker Service
WORKER SERVICE - FEATURE STATUS
# | Feature | Status | Notes
1 | Poll systemlogs table for new rows | DONE | Watermark-based polling, configurable batch size
2 | Parse raw syslog (RFC 5424 PRI) | DONE | Extracts severity, facility, hostname, program
3 | Insert parsed rows into logevent | DONE | Bulk insert per poll cycle
4 | Evaluate alert rules against events | DONE | AlertRuleEvaluator keyword matching
5 | Insert fired alert events | DONE | Creates alertevent rows for triggered rules
6 | Metric accumulation + flush | DONE | Thread-safe counters to systemmetric table
7 | Seed default alert rules | DONE | 5 default rules on first run
8 | Clean Python b wrapper artifacts | DONE | Fixes dirty import data
9 | Source matching (IP/hostname to source) | DONE | Associates events with source.Id
10 | Complex conditions (AND/OR/threshold) | PARTIAL | Only keyword matching - no threshold/window/rate
11 | Notification dispatch (email/SNMP/webhook) | NOT STARTED | Alert fires but no notification sent
12 | Export job processing | NOT STARTED | ExportJobDto exists, no worker logic
13 | Source health monitoring (online/offline) | NOT STARTED | No heartbeat or staleness detection
14 | Log rotation / archival jobs | NOT STARTED | No scheduled maintenance tasks

## Missing Backend
MISSING BACKEND FEATURES (No API exists yet)
# | Feature | Needed For | Priority | Complexity | Assigned To
1 | SSO / Active Directory integration | Homepage SSO button | LOW | HIGH
2 | Real TOTP/MFA implementation | Homepage MFA screen | MEDIUM | MEDIUM
3 | Password reset flow | Homepage forgot password | MEDIUM | MEDIUM
4 | Notification channels CRUD API | Settings > Notifications, Alert actions | HIGH | MEDIUM
5 | Notification dispatch service | Alert rule firing | HIGH | HIGH
6 | Export job API + worker processing | Search CSV export, Feed export | MEDIUM | MEDIUM
7 | Source groups CRUD API | Sources > Groups tab | MEDIUM | LOW
8 | Protocol/listener management API | Sources > Protocols tab | LOW | HIGH
9 | Parser configuration CRUD API | Sources > Parsers tab | LOW | HIGH
10 | TLS certificate management API | Settings > Network | LOW | HIGH
11 | API key generation + management | Settings > API Keys | LOW | MEDIUM
12 | Audit log recording | Settings > Audit Log | MEDIUM | MEDIUM
13 | License management API | Settings > License | LOW | LOW
14 | LDAP/AD user sync | Settings > Users | LOW | HIGH
15 | Source health/heartbeat detection | Sources table status | MEDIUM | MEDIUM
16 | Event trend calculation (% change) | Dashboard KPI arrows | LOW | LOW
17 | Faceted search (counts per facet) | Search facet sidebar | MEDIUM | MEDIUM
18 | Heatmap data API (hour x day) | Analytics heatmap | LOW | MEDIUM
19 | Security event categories API | Analytics categories | LOW | MEDIUM
20 | Storage growth history API | Storage growth chart | LOW | LOW

## Roadmap
IMPLEMENTATION PRIORITY ROADMAP
Priority | Module | Key Items | Est. Effort | Assigned To
P0 - Critical | Alerts | New Rule modal, Edit modal, toggle switch, notification channels | 3-4 days
P0 - Critical | Sources | Add Source modal, Detail panel, toolbar filters, pagination | 3-4 days
P0 - Critical | Search | Keyword filter, Severity dropdown, Facet sidebar, CSV export | 2-3 days
P0 - Critical | Live Feed | Search bar, Source/Time filters, Facility column, footer stats | 1-2 days
P1 - High | Dashboard | Donut chart, Source Types panel, Device Health, trend arrows | 2-3 days
P1 - High | Users | Invite User modal, role editing, MFA toggle, auth policy | 2-3 days
P1 - High | Worker | Notification dispatch (email), threshold-based conditions | 3-4 days
P1 - High | CSS/Modals | Modal overlay system, toggle switches, filter tags, slide panels | 2-3 days
P2 - Medium | Analytics | Heatmap, Security Categories, line chart, bucket controls | 2-3 days
P2 - Medium | Storage | Rotation schedule table, growth chart, progress bars | 1-2 days
P2 - Medium | Notifications | SMTP/SNMP/Webhook settings pages with test buttons | 2-3 days
P2 - Medium | Audit Log | Log entries list, filters, export | 1-2 days
P3 - Low | Sources Groups | Group cards grid, CRUD API | 1-2 days
P3 - Low | Sources Protocols | Listening ports table, Network ACL panel | 2-3 days
P3 - Low | Sources Parsers | Parser cards, drag ordering, test parser | 3-4 days
P3 - Low | Network/TLS | Certificate management, listener bindings | 2-3 days
P3 - Low | API Keys | Key generation, integrations grid | 1-2 days
P3 - Low | License | Usage bars, key display, danger zone | 1 day
P3 - Low | Homepage | SSO, real MFA, ticker animation, forgot password | 2-3 days

## Scorecard
SUMMARY SCORECARD
Category | Total | Implemented | Partial | Stub/Missing | % Complete
UI Pages | 20 | 2 | 10 | 8 | 45%
API Endpoints | 40 | 39 | 1 | 0 | 98%
Worker Features | 14 | 9 | 1 | 4 | 68%
Homepage Components | 14 | 4 | 4 | 6 | 43%
Dashboard Components | 9 | 5 | 0 | 4 | 56%
Live Feed Components | 15 | 7 | 1 | 7 | 50%
Search Components | 17 | 5 | 1 | 11 | 32%
Alerts Components | 11 | 3 | 1 | 7 | 32%
Sources Components | 15 | 3 | 0 | 12 | 20%
Settings Components | 29 | 4 | 0 | 25 | 14%
Missing Backend APIs | 20 | 0 | 0 | 20 | 0%
OVERALL PROJECT COMPLETION
UI (match mockups) | 40%
API Backend | 95%
Worker Service | 65%

## Database
DATABASE ENTITIES & TECH STACK
# | Entity / Table | Used By | Status
1 | systemlogs (public.logs) | Worker input - raw syslog from NXLog | ACTIVE
2 | logevent | Worker output - parsed events | ACTIVE
3 | logsource | Sources inventory | ACTIVE
4 | alertrule | Alert rule definitions | ACTIVE
5 | alertevent | Fired alert events | ACTIVE
6 | appuser | User accounts | ACTIVE
7 | userrole | User-role assignments | ACTIVE
8 | role | Role definitions | ACTIVE
9 | usersession | JWT refresh token sessions | ACTIVE
10 | platformsetting | General settings | IN-MEMORY ONLY
11 | storagepolicy | Retention policies | ACTIVE
12 | systemmetric | Worker metric snapshots | ACTIVE
13 | exportjob | Export job queue | SCHEMA ONLY
TECH STACK
Component | Technology | Version | Notes
Backend API | ASP.NET Core | .NET 8 | REST API with Swagger
WebUI | ASP.NET Core MVC | .NET 8 | Razor views
Worker | BackgroundService | .NET 8 | Windows Service / Console
Database | PostgreSQL | AWS RDS | Npgsql + EF Core
Auth | JWT Bearer + BCrypt | - | Refresh token rotation
Charts | Chart.js | v4 | CDN loaded
CSS | Custom (sentinel.css) | - | CSS custom properties
Log Ingestion | NXLog > PowerShell > PostgreSQL | - | Import-Logs-debug.ps1